## Slide 1: SOCIAL MEDIA USING CHATBOT
UMMU HABEEBA T
20MCA11058
Product Owner
NOWSHAD C V
Assistant Professor
Department of Computer Application
MES COLLEGE OF ENGINEERING, Kuttipuram

## Slide 2
Table Of Contents:
1. Description
2. Modules
3. Developing Environment
4. Product backlog
5. User story
6. Project plan
7. Sprint plan
8. Sprint1 Actual

## Slide 3: SOCIAL MEDIA USING CHATBOT
It is to form an intelligent AIML based chatbot that may allow a person's interacting with the bot to possess an ongoing, interesting and enriched conversation featuring searched information from Google.
It is we'll attempt to build a chatbot that may incorporate a standard sense dataset to supply simple but relevant responses while chatting.
An AI chatbot is instruct to work more or less on its own, employing a process referred to as Natural Language Processing, or NLP, is combined with AI and therefore the annotation of human data.
AI chatbots get smarter over time

## Slide 4: Developing Environment
Hardware Requirements:
Processor: i3
Hard Disk: 500 GB
RAM: 4 GB
Software Requirements:
Language: Python
Front End: Python- django
Back end: SQlite
Dataset: nltk Corpus.
Techniques Used: Cosine Similarity .
IDE: Visual Studio Code , Anaconda Navigator
OS: Windows/Linux

## Slide 5: MODULES
1.Admin
Administration
2 Functions of user
Registration
Login
Manage profile , Post & Friends
Can chat with chatbot

## Slide 6
User Story
User Story ID | As a <Type Of User> | I Want to <Perform some Task> | So That I Can <Achieve Some Goal>
1 | User | Collection of Social media corpus from nltk site | Social media corpus
2 | User | Rank highest Frequent Data | Ranking
3 | User | Find Cosine Similarity Of highest Ranked Data | Highest Ranked Data
4 | User | UI Creation Model creation(Registration & Login form) | Linking With Data Base
5 | User | Home Page Creation | Create Home Page for Social Media
6 | User | Manage Post (Add/Delete/Edit/View) | Can Manage Post
7 | User | UI Creation (Send/Manage Friend Request) | Can Manage Friends
8 | User | Design Correction After Integration | Well Design
9 | User | Create Chat Interface | Chat Interface
10 | User | Collect User Query From Chat Interface | Collect user Queries
11 | User | Apply Cosine similarity Algorithm on User Query & Find highest Similarity | Find Response
12 | User | Return Highest similar Answer as Response | Get accurate result

## Slide 7
User story ID | Priority<High/ medium/Low> | Size(hours) | Sprint<#> | Status<Planned /In progress/ Completed> | Release Date | Release Goal
1 | Medium | 2 | 1 | Completed | 28/12/2021 | Collection of Social media corpus from nltk site
2 | medium | 5 |  | Completed | 29/12/2021 | Rank highest Frequent Data
3 | High | 3 |  | Completed | 10/1/2022 | Find Cosine Similarity Of highest Ranked Data
4 | Medium | 3 | 2 | Planned | 01/01/22 | UI Creation Model creation(Registration & Login form)
5 | Medium | 2 |  | Planned | 01/01/22 | Home Page Creation
6 | Medium | 5 |  | Planned | 16/01/22 | Manage Post (Add/Delete/Edit/View)
7 | Medium | 5 | 3 | Planned | 22/01/22 | UI Creation (Send/Manage Friend Request)
8 | Medium | 5 |  | Planned | 23/01/22 | Design Correction After Integration
9 | Medium | 5 | 4 | Planned | 30/01/22 | Create Chat Interface
10 | High | 5 |  | Planned | 05/02/22 | Collect User Query From Chat Interface
11 | High | 5 |  | Planned | 12/02/22 | Apply Cosine similarity Algorithm on User Query & Find highest Similarity
12 | High | 5 |  | Planned | 12/02/22 | Return Highest similar Answer as Response
Product Backlog

## Slide 8
User Story ID | Task Name | Start Date | End Date | Days | Status
1 | Sprint 1 | 27/12/21 | 27/12/21 | 2 | completed
2 |  | 27/12/21 | 27/12/21 |  | completed
3 |  | 28/12/21 | 28/12/21 |  | completed
4 | Sprint 2 | 29/12/21 | 30/12/21 | 4 | completed
5 |  | 01/01/22 | 01/01/22 |  | completed
6 |  | 16/01/22 | 16/01/22 |  | planned
7 | Sprint 3 | 22/01/22 | 22/01/22 | 4 | planned
8 |  | 23/01/22 | 23/01/22 |  | planned
9 | Sprint 4 | 29/01/22 | 29/01/22 | 4 | planned
10 |  | 30/01/22 | 30/01/22 |  | planned
11 |  | 05/02/22 | 05/02/22 |  | planned
12 |  | 12/02/22 | 12/02/22 |  | planned
Project Plan

## Slide 9
SPRINT PLAN
Backlog Item | Status and Completion date | Original Estimate in hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 8 |  |  | y 11
User Story #1 |  |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  |  | 
Backlog item | Status & Completion date | Original Estimate in hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
User Story#1,2,3 |  |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
Data set creation | 28/12/2021 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ranking& find C S | 10/01/2022 | 8 | 3 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User story #4,5,6 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UI designing & Manage post | 16/01/2022 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
User story #7,8 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design Correction after Integration | 23/01/2022 | 10 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1
User story #9,10,11 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chatbot & Output | 12/02/2022 | 20 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 1
Total |  | 50 | 10 | 4 | 7 | 3 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 2

## Slide 10
SPRINT1 ACTUAL
Backlog item | Status & Completion date | Original Estimate in hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
User Story#1,2,3 |  |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
Data set creation | 28/12/2021 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ranking& find C S | 10/01/2022 | 8 | 3 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User story #4,5,6 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UI designing & Manage post | 16/01/2022 |  |  |  |  |  |  |  |  |  |  |  |  | 
User story #7,8 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design Correction after Integration | 23/01/2022 |  |  |  |  |  |  |  |  |  |  |  |  | 
User story #9,10,11 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chatbot & Output | 12/02/2022 |  |  |  |  |  |  |  |  |  |  |  |  | 
Total |  | 50 | 5 | 0 | 3 | 0 | 2 |  |  |  |  |  |  | 

## Slide 11: THANK YOU