## Slide 1: DATA MINER AND ANALYSER FOR ECOMMERCE
MOHAMMED AJNAS K
MES20MCA-2027
PRODUCT OWNER: MR. VASUDEVAN T V

## Slide 2: TABLE OF CONTENTS
Introduction
Modules
Data Flow Diagram
Developing Environment
Product Backlog
User Stories
Project Plan
Sprint Plans
Sprint Actual

## Slide 3: Introduction And Objectives
Introduction:
In today where people prefer shopping online rather than traditionally so we need system which saves our time and
money.These large number of ecommerce website put users in turmoil to search and choose to buy a single product
from multiple ecommerce website.With the system a customer will simply search for the product he wants and the
system will mine the web and display the same product from several websites.The proposed solution helps online
users to grab best deal for their product from multiple ecommerce websites on single web interface.
Objectives:
• Our objective here is to build a system which will provide the customer with the same
product from different websites at one place
• it will help the customer compare and decide as to which will be the best option for them thus making their shopping experience faster and more efficient
• The DATA MINER AND ANALYSER FOR ECOMMERCE SYSTEM will recommend the appropriate product to the customer in an automated manner which will save time and money

## Slide 4: MODULES
User Modules
User
  Registration
  Login
  Search Product
  View the product detail
  Go to the product page

## Slide 5: DATA FLOW DIAGRAM
LEVEL 0
LEVEL 1.1

## Slide 6: DEVELOPING ENVIRONMENT
Hardware Requirements
Processor - Intel x86
Speed - 1.1 GHz
RAM - 4 GB (min)
Hard Disk - 50 GB
Software Requirements
Operating System - Windows 7 or Above ,Android
Frontend – Html/Css,Python
Backend – SQlite3
IDE-Pycharm
Web Browser - Google Chrome
Frame work - Flask

## Slide 7: PRODUCT BACKLOG
User Story ID | Priority <High/Medium/Low> | Size (Hours) | Sprint <#> | Status <Planned/In progress/Completed> | Release Date | Release Goal
1 | Medium | 2 | 1 | Completed | 08/01/2022 | Table design
2 | High | 3 |  | Completed | 08/01/2022 | Form design
3 | High | 5 |  | Completed | 08/01/2022 | Basic coding
4 | High | 6 | 2 | Planned |  | Collecting data from flipkart
5 | Medium | 6 |  | Planned |  | Add the data to database
6 | High | 7 | 3 | Planned |  | Collecting data from amazon
7 | high | 6 |  | Planned |  | Add the data to database
8 | Medium | 5 | 4 | Planned |  | Taking accurate data from database
9 | Medium | 5 |  | Planned |  | Testing data
10 | High | 5 |  | Planned |  | Output generation

## Slide 8: USER STORIES
UserStoryID | As a <type of user> | I want to | So that I can
1 | User | login | login successful with correct username and password
2 | User | Registration | user's can register with this webpage
3 | User | Search Product | Search product from ecommerce website and add to the database
4 | User | View the product detail | We can see the product detail from different ecommerce website
5 | User | Go to the product page | We can go to the product page which you like and you can buy

## Slide 9: PROJECT PLAN
User Story ID | Task Name | Start Date | End Date | Days | Status
1 | Sprint 1 | 26/12/2021 | 28/12/2021 | 2 | Completed
2 |  | 29/12/2021 | 31/12/2021 | 3 | Completed
3 |  | 03/12/2021 | 08/01/2022 | 5 | Completed
4 | Sprint 2 | 09/01/2022 | 16/01/2022 | 8 | Planned
5 |  | 17/01/2022 | 21/01/2022 | 5 | Planned
6 | Sprint 3 | 23/01/2022 | 27/01/2022 | 5 | Planned
7 |  | 28/01/2022 | 03/02/2022 | 7 | Planned
8 | Sprint 4 | 04/02/2022 | 08/01/2022 | 5 | Planned
9 |  | 09/02/2022 | 12/02/2022 | 4 | Planned
10 |  | 13/02/2022 | 17/02/2022 | 5 | Planned

## Slide 10: SPRINT BACKLOG PLAN
Backlog Item | Status & completion date | Original estimate in hours | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
User story #1,#2,#3 |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs
Table design | 28/12/2021 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Form design | 31/12/2021 | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Coding | 08/01/2021 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
User story 4,5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Collecting data from flipkart | 16/01/2022 | 6 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Add the data to database | 21/01/2022 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0
User story 6,7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Collecting data from amazon | 27/01/2022 | 7 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add the data to database | 03/02/2022 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 1 | 1 | 0 | 0
User story 8,9,10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Taking accurate data from database | 08/01/2022 | 5 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing data | 12/02/2022 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0
Output generation | 17/02/2022 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 1
Total |  | 50 | 6 | 5 | 3 | 2 | 4 | 5 | 0 | 4 | 4 | 5 | 3 | 4 | 3 | 2

## Slide 11: SPRINT ACTUAL
Backlog Item | Status & completion date | Original estimate in hours | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
User story #1,#2,#3,#4 |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs | hrs
Table design | 28/12/2021 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Form design | 31/12/2021 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Coding | 08/01/2021 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
User story #5,#6,#7,#8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Scan files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Text –to-speech |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Speech-to-text |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Save files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
User story #9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Output generation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total |  | 10 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1

## Slide 12
THANK YOU